OUTLINE OF BONDING PROCESS

PARTICIPANTS

- Developer and Developer’s Counsel.

- Bond Counsel (usually acts as special counsel to the Issuer).

- Issuer and Issuer’s Counsel.

- Credit Enhancer and Credit Enhancer’s Counsel.

- Tax Credit Purchaser and Tax Credit Purchaser’s Counsel.

- Bond Trustee and Bond Trustee’s Counsel.

- Underwriter and Underwriter’s Counsel.

A.  PLANNING PHASE (1 month to 12 months)

- Reimbursement/Inducement Resolution adopted by Issuer.

- Application for and receipt of Volume Cap allocation.

- Interview and retain participants.

- Determine bond structure (Private Placement, Public Offering, Fixed or Variable Rate, Credit Enhancement Program).

- Application for Credit Enhancement/purchase and receipt of preliminary approval.

B.  DOCUMENT DRAFTING/DUE DILIGENCE PHASE (1 month to 2 months)

- Drafting and approval of bond documents and terms.

- Drafting of Offering/Sale Documents.

- Real Estate Due Diligence (appraisals, environmental reports, surveys, etc.).

- Drafting and execution of Construction Contracts and Cost Determination.

- Drafting of Partnership Documents.

C.  SALE AND CLOSING PHASE (2 weeks to 1 month)

- Drafting opinions and closing documents.

- Mailing Offering Documents.

- Public Hearing Notice Publication and Hearing.

- Adoption of Bond Resolution by Issuer.

- Sale of Bonds and Execution of Bond Purchase Agreements.

- Preclosing and Closing (Delivery of executed Documents and Opinions).